## Sheet1
Project Name | E-Commerce Website
Application Version | 5.8
Module | All modules
Created Date | 29-12-2025
Created By | Seema Bagali
Phase | System Testing
TEST CASE ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | PRIORITY | SEVERITY | STATUS | ASSIGNED TO | SCREENSHOT
TC_Signup_02 | User is able to login with invalid credentials | 1.Click on sign up link 2.Enter invalid username & password 3.Click on sign up button | High | Critical | Open | Dev Team
TC_CT_04 | Cart items doesn’t persist after refresh | 1. Add one or more products to the cart 2. Navigate to cart page 3. Refresh the browser | High | Medium | Open | Dev Team
TC_CT_05 | The system allows the user to click Place Order with an empty cart and does not display any error message. | 1.Open the Cart page 2.Ensure no products are added 3.Click on the Place Order button | High | Critical | Open | Dev Team
TC_CO_04 | The system does not show any validation or error message when invalid card number or expiry date is entered during checkout. | 1.Add a product to the cart 2.Click Place Order 3.Enter invalid card number or expired card date4.Click Purchase | High | High | Open | Dev Team
TC_CF_03 | The Contact form accepts invalid email formats without displaying an error or validation message. | 1.Open Contact modal 2.Enter invalid email (e.g., test@) 3.Click Send Message | Medium | Medium | Open | Dev Team
TC_CF_04 | The Contact form allows submission when mandatory fields are left blank and does not show validation messages. | 1.Open Contact modal 2.Leave Name or Message field empty 3.Click Send Message | Medium | Medium | Open | Dev Team